## Sheet1
Risk # | Risk | Reqt. | Type | Description | Likelihood | Consequence | Risk Reduction Plan
1.1 | Paint without damaging field | MNFR7 | Programmatic | Paint damages the field or robot paints erratically | 3 | 5 | Use a water-soluble paint or another bio-degredable solution
1.2 | Create custom reliable paint assembly | MNFR6, MNFR7 | Technical, Schedule | Paint mechanism fails to meet requiremnts or becomes unreliable | 4 | 4 | Develop and test a proven solution such as aerosol cans. Sacrifice paint capacity.
2.1 | Reliable mobile application as GUI | DNFR2 | Schedule | Mobile app freezes or constantly loses communication with system. Time required to learn how to write an app in a mobile device | 5 | 2 | Use a laptop or create a GUI in a laptop
2.2 | Real-time reaction to commands | MFR5, MFR6, MNFR5 | Technical | System too slow to detect user command or ignores user commands. | 4 | 5 | Synchronize clocks between computers
3.1 | Maintain high accuracy and precision | MFR1, MFR2 | Programmatic | System is unable to paint consistently or system cannot meet accuracy standards needed | 3 | 4.5 | Add redundant sensors and improve sensor fusion. Filter noise by implementing a filter. Add multiple stations that help the system triangulate.
3.2 | Maintain reliable localization | MNFR1, MNFR2 | Cost | Fails to locate itself during operation or gets conflicting localization errors | 2.5 | 4 | Add multiple localization sensors
4 | Unwanted collision during painting | MFR5 | Schedule | Hits an obstacle that damages the system | 2 | 3 | Able to stop the robot wirelessly or by hitting an E-Stop on-board
5 | Meet design requirements within budget | DNFR1 | Cost, Technical | Design an affordable yet highly reliable platform | 3 | 5 | Sacrifice features to meet major requirements
6 | Slow operation | MNFR5 | Technical | Requires a slow speed to perform full task which reflects the amount of time needed | 5 | 1 | Test to find operational limit. Optimize control parameters.
7 | Grass terramechanics | MFR1, MNFR7 | Technical | High friction between wheels and terrain. Unable to make point turns. Wheels cause unwanted damge to the field | 3 | 2 | Reduce number of contact points with terrain
8.1 | Communication | MFR7 | Technical | Loses communication signal between robot and station. Unable to receive commands or localization feedback. | 2 | 4 | Install a watchdog timer on the control architecture of the robot. If the robot stops receiving commands from the station the robot should stop motion and painting.
8.2 | Clock Synchronization | MFR1, MFR2, MFR4, MFR7, MNFR1, MNFR2, MNFR4 | Technical | On-board CPU, Commnad Station CPU, and Leica Robot Total Staion become out of synch. Causes the system to receive wrong localization data and perform actions according to them. | 5 | 5 | Use additional on-board sensors to mitigate lost of localization. Synchronize CPU clocks from a known data sample.
8.3 | Localization feedback data refresh rate | MNFR1, MNFR2, MNFR5 | Technical | Refresh rate of localiztion feedback is too slow for the system to accurately paint the field | 5 | 3 | Move and paint at a slower pace than desired. Use on-board sensor data to increase speed of painting job.
9 | Unpredicted error system | MNFR3 | Technical | Random technical error with the system. Requires technial expertise to solve the problem | 3 | 2 | Perform several tests to increase robustness. Have a trained team member solve the technical tasks.