## Spring
Fieldroid |  |  | PR7 | PR8 | PR9 | SDevR
|  |  | PR10 | PR11 | FSD | FSDE | Period Highlight: |  |  |  |  | 11 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) | [8 empty] | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | J a n u a r y |  |  |  |  | s | su | m | t | w | th | f | s | su | m | t | w | t | f |  | F e b r u a r y |  |  |  |  | f | s | su | m | t | w | th | f | s | su | m | t | w | th | f | s | su | m | t | w | th | f |  | M a r c h |  |  |  | th | f | s | su | m | t | w | th | f | s | su | m | t | w | th | f | s | su | m | t | w | th | f | s | su | m |  | A p r i l |  |  |  | su | m | t | w | th | f | s | su | m | t | w | th | f | s | su | m | t | w | th | f
ACTIVITY | Owner | START | DURATION | START | DURATION | COMPLETE | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
[6 empty] | Day # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103
Serial Communication w/ Motor Con. | J | 1 | 12 | 1 | 12 | 90%
Order new PCB, parts | A | 1 | 8 | 1 | 8 | 90%
IMU Communication Dem | J | 1 | 19 | 1 | 19 | 30%
Consult PID Experts | M | 1 | 10 | 1 | 10 | 100%
User App Basic GUI | S | 1 | 10 | 1 | 10 | 100%
Paint on Grass | M | 1 | 15 | 1 | 15 | 100%
Test Logistics | A | 11 | 23 | 11 | 23 | 0%
App Bluetooth Comm | S | 11 | 15 | 11 | 15 | 0%
Meet with Nathan | M | 11 | 6 | 11 | 6 | 10%
Serial Comm w/ Code | S | 10 | 5 | 10 | 5 | 50%
Fix Motor Controller | A | 8 | 15 | 8 | 15 | 10%
IMU Integration w/ Software System | J | 15 | 19 | 15 | 19 | 0%
Submit Last PCB Design | A | 25 | 9 | 25 | 9 | 0%
Closed Loop on Blocks | S | 17 | 7 | 17 | 7 | 0%
MJT - Straight Line | M | 11 | 16 | 11 | 16 | 0%
MJT - Curves | M | 20 | 14 | 20 | 14 | 0%
Cleaning Code | M | 11 | 23 | 11 | 23 | 0%
2nd PCB Iteration Working | A | 20 | 9 | 20 | 9 | 0%
Derivative Control | M | 11 | 23 | 11 | 23 | 0%
Case Design Iteration 1 and Printed | J | 5 | 43 | 5 | 43 | 0%
Outdoors Testing | M | 30 | 18 | 30 | 18 | 0%
Smooth Velocity | M | 26 | 22 | 26 | 22 | 0%
Beagle Bone Controlled with App | S | 26 | 22 | 26 | 22 | 0%
Connected Points - Quadratic Progr. | M | 34 | 14 | 34 | 14 | 0%
Localization Kinematic Transformation | M | 34 | 14 | 34 | 14 | 0%
Start on Boot with Switch | J | 10 | 33 | 10 | 33 | 0%
Wireless E-Stop | A | 8 | 35 | 8 | 35 | 0%
Integrate Last PCB Design | A | 34 | 19 | 34 | 19 | 0%
Case Design Iteration 2 and Printed | J | 40 | 14 | 40 | 14 | 0%
Code Integration (new control) | M | 34 | 16 | 34 | 16 | 0%
Full Field Outline | MS | 40 | 14 | 40 | 14 | 0%
Testing/Validation | MA | 40 | 29 | 40 | 29 | 0%
Cleaner App Interface | S | 48 | 21 | 48 | 21 | 0%
Final Case Design | J | 54 | 12 | 54 | 12 | 0%
Test/Validation | ALL | 69 | 26 | 69 | 26 | 0%
Test/Validation | ALL | 95 | 9 | 95 | 9 | 0%

## Fall
Fieldroid |  | PR1 | PR2 | PR3 | PR4
|  | PR5 | PR6 | 2nd Sem | Spr. Test | Period Highlight: |  |  |  |  | 60 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) | [8 empty] | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | S e p t e m b e r | [8 empty] | O c t o b e r |  |  |  |  | m | [6 empty] | m | [6 empty] | m | [6 empty] | m |  |  |  |  | N o v e m b e r | [8 empty] | m | [6 empty] | m | [6 empty] | m | [6 empty] | D e c e m b e r | [6 empty] | m | [5 empty] | J a n |  |  | F e b |  |  |  | M a r |  |  |  |  | A p r |  |  |  | M a y
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | -> | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18
[5 empty] | Day # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102
Systems Planning | 1 | 5 | 1 | 5 | 100%
Order Sensors | 1 | 10 | 3 | 10 | 100%
Order Wheels | 2 | 9 | 4 | 7 | 100%
Order Motors | 3 | 8 | 4 | 7 | 100%
Order CPU | 4 | 7 | 5 | 11 | 100%
Draft CAD Drawings | 3 | 10 | 7 | 10 | 100%
Chasis Design | 9 | 8 | 9 | 10 | 100%
Order Power Systems | 11 | 6 | 11 | 6 | 100%
Survey Gun Test Validation | 15 | 7 | 18 | 5 | 100%
Design Paint System | 14 | 18 | 14 | 18 | 100%
Order Paint Parts | 29 | 5 | 29 | 5 | 100%
Survey Gun Data Validation | 23 | 10 | 23 | 10 | 100%
Radio to Radio Communication | 18 | 20 | 18 | 20 | 100%
Chasis Construction | 13 | 12 | 20 | 16 | 100%
Power Board Development | 14 | 32 | 14 | 32 | 100%
Motor Control from CPU | 10 | 36 | 12 | 34 | 100%
Survey Gun/CPU Communication | 31 | 15 | 31 | 22 | 100%
PID/Encoder Motor Integration | 41 | 14 | 45 | 15 | 100%
Motion Planning (Square) | 36 | 15 | 36 | 20 | 100%
Paint System Construction | 37 | 14 | 37 | 14 | 100%
IMU Integration | 83 | 15 | 83 | 15 | 0%
Painting Rectangle | 43 | 21 | 43 | 21 | 100%
Motion Planning Software | 46 | 12 | 51 | 13 | 100%
Mount All Parts | 34 | 23 | 34 | 23 | 100%
Paint Mini Field | 43 | 15 | 43 | 29 | 100%
Leica Integration | 59 | 6 | 59 | 9 | 100%
User Interface | 83 | 10 | 83 | 1 | 0%
Tracking Prism Development | 84 | 18 | 84 | 1 | 0%
Tunning and Readjustment | 84 | 9 | 84 | 1 | 0%
Reassessment | 84 | 18 | 84 | 1 | 0%
Paint Full Scale Field w/ UI | 84 | 18 | 84 | 1 | 0%