## Sheet1
Risk # | Risk | Reqt. | Type | Description | Likelihood | Consequence | Risk Reduction Plan | Status
1 | Paint without damaging field | MNFR7 | Programmatic | Paint damages the field or robot paints erratically | 3 | 5 | Use a water-soluble paint or another bio-degredable solution | 2nd semester
2 | Create custom reliable paint assembly | MNFR6, MNFR7 | Technical, Schedule | Paint mechanism fails to meet requiremnts or becomes unreliable | 4 | 4 | Develop and test a proven solution such as aerosol cans. Sacrifice paint capacity. | SOLVED
3 | Reliable mobile application as GUI | DNFR2 | Schedule | Mobile app freezes or constantly loses communication with system. Time required to learn how to write an app in a mobile device | 5 | 2 | Use a laptop or create a GUI in a laptop | 2nd semester
4 | Real-time reaction to commands | MFR5, MFR6, MNFR5 | Technical | System too slow to detect user command or ignores user commands. | 4 | 5 | Synchronize clocks between computers | 2nd semester
5 | Maintain high accuracy and precision | MFR1, MFR2 | Programmatic | System is unable to paint consistently or system cannot meet accuracy standards needed | 3 | 4.5 | Add redundant sensors and improve sensor fusion. Filter noise by implementing a filter. Add multiple stations that help the system triangulate. | Undergoing…
6 | Maintain reliable localization | MNFR1, MNFR2 | Cost | Fails to locate itself during operation or gets conflicting localization errors | 2.5 | 4 | Add multiple localization sensors | Undergoing…
7 | Unwanted collision during painting | MFR5 | Schedule | Hits an obstacle that damages the system | 2 | 3 | Able to stop the robot wirelessly or by hitting an E-Stop on-board | 2nd semester
8 | Meet design requirements within budget | DNFR1 | Cost, Technical | Design an affordable yet highly reliable platform | 3 | 5 | Sacrifice features to meet major requirements | Undergoing…
9 | Slow operation | MNFR5 | Technical | Requires a slow speed to perform full task which reflects the amount of time needed | 5 | 1 | Test to find operational limit. Optimize control parameters. | SOLVED
10 | Grass terramechanics | MFR1, MNFR7 | Technical | High friction between wheels and terrain. Unable to make point turns. Wheels cause unwanted damge to the field | 3 | 2 | Reduce number of contact points with terrain | 2nd semester
11 | Communication | MFR7 | Technical | Loses communication signal between robot and station. Unable to receive commands or localization feedback. | 2 | 4 | Install a watchdog timer on the control architecture of the robot. If the robot stops receiving commands from the station the robot should stop motion and painting. | SOLVED
12 | Clock Synchronization | MFR1, MFR2, MFR4, MFR7, MNFR1, MNFR2, MNFR4 | Technical | On-board CPU, Commnad Station CPU, and Leica Robot Total Staion become out of synch. Causes the system to receive wrong localization data and perform actions according to them. | 5 | 5 | Use additional on-board sensors to mitigate lost of localization. Synchronize CPU clocks from a known data sample. | 2nd semester
13 | Localization feedback data refresh rate | MNFR1, MNFR2, MNFR5 | Technical | Refresh rate of localiztion feedback is too slow for the system to accurately paint the field | 5 | 3 | Move and paint at a slower pace than desired. Use on-board sensor data to increase speed of painting job. | SOLVED
14 | Unpredicted error system | MNFR3 | Technical | Random technical error with the system. Requires technial expertise to solve the problem | 3 | 2 | Perform several tests to increase robustness. Have a trained team member solve the technical tasks. | Undergoing…
15 | Unable to stop during an emergency | MFR6, MNFR7 | Technical | Robot does not recognize e-stop command and keeps on moving/damaging the environment. | 2 | 3 | Integrate a hardware e-stop with the robot to control power to the drive system (ie locomotion). | SOLVED
16 | Traces of PCB board tear off | MFR1 | Technical, Cost | PCB traces are too thin to conduct the 6.6A of the on-board electronics at the testing temperature. The traces are likely to tear off the PCB board rendering the on-board electronics useless. | 4 | 5 | (Short-term): Use the 12VDC battery to power the pump separetely from the on-board electronics. (Long-term): make a new PCB board with bigger ground traces. | SOLVED (short term)
17 | Runs out of paint | MFR1, MNFR6 | Technical, Cost | Robot takes longer than expected and ends up consuming more resources than expected to paint the field. Robot will then require a refill of resources. | 2 | 3.5 | Calculate the paint consumption rate (0.3038 gal/min). Use the consumption rate and assign an average speed to compute the entire length of time needed to paint a soccer field. Ensure that the robot can hold the entire "predicted" volume of paint to be consumed and a little extra (20% more). | SOLVED
18 | Motor controller USB connection breaks loose again | MFR1 | Technical, Cost | The USB comm port of the RoboteQ loses connection and breaks loose again. The computer is then unable to send control commands to the robot making the robot require an e-stop or abort. | 3 | 3