## Sheet1
Risk # | Risk | Reqt. | Type | Description | Likelihood | Consequence | Risk Reduction Plan
1.1 | Paint without damaging field |  | Programmatic | Paint damages the field or robot paints erratically | 3 | 5 | Use a water-soluble paint or another bio-degredable solution
1.2 | Create custom reliable paint assembly |  | Technical, Schedule | Paint mechanism fails to meet requiremnts or becomes unreliable | 4 | 4 | Develop and test a proven solution such as aerosol cans. Sacrifice paint capacity.
2.1 | Reliable mobile application as GUI |  | Schedule | Mobile app freezes or constantly loses communication with system. Time required to learn how to write an app in a mobile device | 5 | 2 | Use a laptop or create a GUI in a laptop
2.2 | Real-time reaction to commands |  | Technical | System too slow to detect user command or ignores user commands | 4 | 5 | Synchronize clocks between computers
3.1 | Maintain high accuracy and precision |  | Programmatic | System is unable to paint consistently or system cannot meet accuracy standards needed | 3 | 4.5 | Add redundant sensors and improve sensor fusion. Filter noise by implementing a filter. Add multiple stations that help the system triangulate.
3.2 | Maintain reliable localization |  | Cost | Fails to locate itself during operation or gets conflicting localization errors | 2.5 | 4 | Add multiple localization sensors
4 | Unwanted collision during painting |  | Schedule | Hits an obstacle that damages the system | 2 | 3 | Able to stop the robot wirelessly or by hitting an E-Stop on-board
5 | Meet design requirements within budget |  | Cost, Technical | Design an affordable yet highly reliable platform | 3 | 5 | Sacrifice features to meet major requirements
6 | Slow operation |  | Technical | Requires a slow speed to perform full task which reflects the amount of time needed | 5 | 1 | Test to find operational limit. Optimize control parameters.
7.1 | Grass terramechanics |  | Technical | High friction between wheels and terrain. Unable to make point turns | 3 | 2 | Reduce number of contact points with terrain
7.2 | Communication |  | Technical | Loses communication signal between robot and station. Unable to receive commands or localization feedback. | 2 | 4 | Install a watchdog timer on the control architecture of the robot. If the robot stops receiving commands from the station the robot should stop motion and painting.